## StatusReport
Date | ResourceName | Role | ResourceEmail | TaskStatus | TaskAssigned | TaskCompleted | TaskPending | HoursLogged | NextNeededAction | ResponsiblePerson | Clarifications | Risk | Comment
2018-08-28 | Shankar | Developer | kchandru05@gmail.com | Completed | 1. Req1 Design 2. Req1 Coding 3. Unit Testingf | 1. Req1 Design 2. Req1 Coding 3. Unit Testingf |  | 9 | Ready for Testing | Testing
2018-08-28 | Chandru | Tester | chandru.karunanithi@gramenerit.com | Completed | Defect Retesting of Project ABC | Defect Retesting of Project ABC |  | 8 | UAT Testing | UATTesting |  | XYZ Requirement details not shared yet | Will be on leave next week
2018-08-28 | Chandru | Tester | chandru.karunanithi@gramenerit.com | In_progress | 1. abc 2. xyz 3. Test Creation for req1 of project ABC 4. Test Execution for req1 of project ABC | 1. Test Creation for req1 of project ABC 2. Test Execution for req1 of project ABC | 1. abc 2. xyz | 8 | Defect Raised | Developer |  | XYZ Requirement details not shared yet | Will be on leave next week
2018-08-28 | Shankar | Developer | kchandru05@gmail.com | Completed | Req2 Coding | Req2 Coding |  | 10
2018-08-21 | Shankar | Developer | kchandru05@gmail.com | Completed | ABC Req 1 Defect Fixing | ABC Req 1 Defect Fixing |  | 8 | Ready for ReTesting | Testing