## TaskList
ReqID | ReqName | Priority | Severity | ReqStatus | Type | StartDate | EndDate | Developer | DStatus | DStartDate | DEndDate | DPercentCompletion | DComments | Tester | TestCaseStatus | TestCaseIdentified | TestExecutionStatus | Defect Status | DefectDetails | TStartDate | TEndDate | TComments
1 | Req1 | High | Critical | New | Completed | 2018-08-19 | 2018-08-21 | chandru.karunanithi@gramenerit.com | Completed | 2018-08-19 | 2018-08-15 |  |  | kchandru05@gmail.com | Completed |  | Completed |  |  | 2018-08-19 | 2018-08-16
2 | Req2 | Medium | Major | In_Progress | CR | 2018-08-19 | 2018-08-22 | kchandru05@gmail.com | Completed | 2018-08-19 | 2018-08-14 |  |  | chandru.karunanithi@gramenerit.com | Not Started |  | Not Started |  |  | 2018-08-19 | 2018-08-15
3 | Req3 | Low | Minor | New | CR | 2018-08-20 | 2018-08-25 | chandru.karunanithi@gramenerit.com | BAReview | 2018-08-20 | 2018-08-11 |  |  | kchandru05@gmail.com | Not Started |  | BAReview |  |  | 2018-08-21 | 2018-08-12
4 | Req4 | High | Trivial | BAReview | CR | 2018-08-21 | 2018-08-29 | kchandru05@gmail.com |  | 2018-08-20 | 2018-08-12 |  |  | chandru.karunanithi@gramenerit.com | Not Started |  | Not Started |  |  | 2018-08-22 | 2018-08-13
5 | Req5 | Medium | Major | New | New Features | 2018-08-22 | 2018-08-28 | chandru.karunanithi@gramenerit.com |  | 2018-08-22 | 2018-08-18 |  |  | kchandru05@gmail.com | Completed |  | Open |  |  | 2018-08-22 | 2018-08-14